# CCM Vietnam field trip report

Hai Phong

26-27April 2018

Table of contents

[CCM Vietnam field trip report 1](#_Toc518173494)

[1. Purpose 2](#_Toc518173495)

[2. Sponsorship situation 2](#_Toc518173496)

[3. Monitoring time 2](#_Toc518173497)

[4. Monitoring location 2](#_Toc518173498)

[5. Overall purpose 2](#_Toc518173499)

[6. Participant 2](#_Toc518173500)

[7. Summary of monitoring results and general recommendations 3](#_Toc518173501)

[7.1 Achieved targets and common observations: 3](#_Toc518173502)

[7.2 Thank 3](#_Toc518173503)

[7.3 Validation of the Global Fund Coordinating Board 3](#_Toc518173504)

[8. Report of each monitoring site 4](#_Toc518173505)

[8.1 Cao Bang city, Cao Bang province 4](#_Toc518173506)

[*8.2* *SCDI project, VUSTA sub-project* 5](#_Toc518173508)

## Purpose

This report is :

1. A summary of the findings of the Oversight Committee during the monitoring visit from 26 – 27April, 2018 ; and
2. Present the recommendations of the Monitoring Committee to the Global Fund Management Committee in Vietnam (VNCCM) for consideration

## Sponsorship situation

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Funding Number | Name | Grant | Status | Latest activty review |
| VNM-T-NTP | Global Fund to Support TB Prevention and Treatment | TB | Being deployed |  |
|  | Global Fund to Support HIV / AIDS Prevention and Treatment | HIV AIDS | Being deployed |  |

## Monitoring time

November 21-22, 2016

## Monitoring location

* Hai Phong
* Hai Phong Department of Health
* SCDI Hai Phong office, VUSTA project
* Methadone center, Le Chan district.

## Overall purpose

* Ensure that activities are implemented as specified in the grant and work plan.
* Understand the quality of service, activity and communication between the provider and the recipient, as well as the stigma surrounding the programs and diseases funded by the Global Fund.
* Monitor the amount of drugs and biologicals present as well as the status of disbursements.
* Shown for the staff and the community to know that state leaders are still concerned about their situation by collecting the opinion relation to programs and disease to build up theirfaith and responsibility

## Participant

Members of the CCM / OC, the Ministry of Health, the CCM Secretariat (as of April 2018) participated in the monitoring visit, the attached list included in appendix B.

## Summary of monitoring results and general recommendations

### Achieved targets and common observations:

The CCM/OC's Apriltrip has reached the general objectives outlined in the fifth provision. The OC noted that activities were implemented in the right place and effectively. The OC will continue to actively assist the localities in 2018. Through the trip, the OC recognizes the quality of services, activities and propaganda between the supplier and the recipient.

Generally most recipients are doing well. A number of general recommendations for PR are outlined in the following pages. A summary of the findings from the visit at each site included specific recommendations for PRs / recipients of aid along with indicators in the timeframe are set out in section 8.

### Thank

CCM - The Oversight Committee would like to thank the support the delegation received for this monitoring visit. The group would like to thank Hai Phong Department of Health, HIV and TB PMUs at the province as well as in Central. CCM - OC would like to thank the PRs for their helpful and thoughtful preparation in developing the trip program.

The CCM - OC would also like to thank all the delegates who attended and shared their thoughts and experiences in contributing to the CCM proposals - committees and advisers before, during and after.

### Validation of the Global Fund Coordinating Board

|  |
| --- |
| Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  Signature:\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  *Approved and Signed*  Prof. Trinh QuanHuan  CCM Chairman |

## Report of each monitoring site

The following report will detail the work at each site of the CCM - OC. The specific reports of each project are attached to this minutes.

### Cao Bang city, Cao Bang province

#### Overview

CCM - Monitoring Committee planned to have an update on the activities of the HIV/AIDS, TB program in Hai Phong City. The HIV/AIDSPrevention Center is responsible for implementing HIV aid in the province. Hai Phong Hospital for Tuberculosis and Lung Disease is responsible for implementing the TB program.SCDIsub-project is responsible for implementation of VUSTA project in the area. CCM - OC had a working session with the leaders ofHai Phong Health Department; Local project management board leaders and other health workers.

#### Summary observation report and findings on the projects:

***HIV/AIDS project***

* 2017 results
* Improved communication contents, methods with 9610 times in different methods in 2017 for more than 1.5 million people on HIV/AIDS;
* Organized workshops on HIV/AIDS and social evil prevention policies, regulations for sectors, organizations;
* 100% districts were trained and implemented screening test for HIV; 105/223 commune received training on HIV screening test;
* Number of syringes distributed in 2017: 1.211.500;
* Number of condoms distributed in 2017: 729.372;
* Methadone by 31/12/2017: 3950 patients, achieved 86 % of the target;
* 100% districts implemented online reports following Circular 03/2015/BYT;
* Annual monitorings on risk target: IDU, FSW, MSM were carried out as regulated by MOH’
* HIV info; Prevent HIV, ACIS: had been implemented to districts, however there are still limitations during implementation.
* 2018 plan
* Continue the cooperation with SCDI and district health centers to implement damage reduction intervention (communiation, distributing condoms, syringes…)
* Maintain and expand the Methadone network, in 2018 there are 3 new locations to be opened at 3 districts: Le Chan, Tien Lang, Thuy Nguyen;
* Cooperate with the PMUs of HIV/AIDS prevention projects to implement the software system for the management of patients receiving Methadone treatment;
* Extend early treatment through HIV screening at testing areas, community HIV screening areas, self-detect HIV and private HIV testing sight to target community and PLWH’s partners. Organize training for HIV testing for CBO and colaborators;
* Continue to strengthen mother-to-child HIV prevention activities;
* Implement HIV/STIs monitoring in 2018 for FSW and MSM;
* Training to improve health workers’ capacity in monitoring the activities, ensuring the quality of data;
* Implement online health record using ePMS software;
* Cooperate with other programs to implement 90-90-90;
* Cooperate with HPMU to implement the Drive-in project when endorsed by the Central PMU.
* Difficulties
* Human resourse and HIV/AIDS prevention activities;
* Low rate of FSW, MSM taking HIV test and consultant;
* There’re still PLWH not taking ARV treatment;
* Need time to complete, hence may affect the implementation of project’s activities and disbursement;
* 100% of the project’s personel are part-time, which make disbursement difficult.
* Suggestion
* Integrate the implementation of GF’s activities with local health activities, strengthen communication, referring for testing of high-risk subjects; diversify the testing form to allow easier approach;
* Maintain the activities of the project while waiting for endorsement from the People’s Committee;
* Improve technical support regarding specialty and finance to the project’s sites;
* Quickly complete the plan and PMU for the 2018-2020 phase.

***TB project***

* 2017 results
* Drug-resistant TB: Sputum transfer; screening; support for patients: medicine for side-effects, compensation for hospitalization, meals, testing, re-examination; monitoring. Disbursed: 648.299.127/1.375.668(2017)
* HIV screening for TB patients and GeneXpert for HIV patients: quick HIV test for TB patients; PITC maintaining; GeneXpert. Disbursed: 65.830.000/105.180.000 (2017)
* TB screening and prevention for children: IPT prevention for children; active TB screening for children; report. Disburse: 68.250.000/17.790.000 (2017) and 108.810.000 (2016)
* TB-HIV cooperation at provincial and district level. Disbursed: 48.000.000/48.000.000 (2017)
* Screening for early detection for prisoners: screening; Xray; sputum smear; GeneXpert. Disbursed: 105.443.500/106.875.000 (2017)
* Training: Vitimes; drug-resistant TB. Disbursed: 53.890.000/53.890.000 (2017)
* Implement mHealth solution for effective monitoring. Disbursed: 182.400.000/182.400.000 (2017)
* 2018 plan
* Continue the support for drug-resistant TB patients;
* TB screening for children;
* TB screening for HIV patients
* Suggestion:

### Budget is late on delivery to the area, hence affecting the progress of several TB prevention activities.

### *SCDI project, VUSTA sub-project*

* + 1. ***Summary of observations and findings of the project:***
* 2017 results
* In 2017, 4.955/7.074 people were approached for HIV screening, among 73 were confirmed and 68 connected for treatment.Several difficulties for OPC treatment were noted, such as: 1 FSW didn’t want treatment affraiding of disclosing personal information, 1 PWID were so confident of personal health, 3 PWIDs moved away and lost contact;
* HIV consultation at the community (Laytest): there are 30 community testers who are also peers, conducted screening for 267 customers, found 4 reacted cased, transferred for confirming test and treatment;
* In the first Quarter 2018, conducted screening for 108 customers, found 2 reacted cases among MSM patients, transferred for treatment;
* In 2017: 47 small group communication sessions were conducted with 752 participants and 156 group consultation sessions with 1404 participants;
* 1st Quarter/2018: conducted 4 communication sessions for 64 customers and 9 consultation sessions for 90 customers;
* Item distribution

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | **Condom** | **CBT** | **Syringe** | **NC** | **HAT** |
| Item distributed in 2017 | **716.374** | **81.449** | **1.340.410** | **652.599** | **2.199** |
| Customer received the items in 2017 | **7.038** | **1.092** | **4.468** |  |  |
| Item distributed inQ1/2018 | **86.553** | **18.951** | **130.223** | **55.361** | **714** |
| Customer received the items in Q1/2018 | **3.423** | **1.034** | **1.526** | **1.523** |  |

* In the scope of the project, from June-December 2017, SCDI had piloted supporting for 600 HIV patients to receive treatment through their health insurance;
* In 2018, HIV patients support was officialized. Hence, it is expected to be able to support 450 HIV patients who have difficulties in approach HIV treatment in 2018.
* Hai Phong 2017 disbursement result

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Hai Phong | Total budget | Implemented | Remaining | Rate of disbursement |
| 3,840,970,000 | 3,742,510,771 | 98,459,229 | 97% |

* Difficulties
* Low support for collaborators, unstable personel, capacities between members of the group are not the same;
* Less capacity improvement activities;
* Some groups have difficulties using PC which affected the management, follow-up and recording of the group’s data.
* Suggestion
* PAC to continue the support for capacity improvement for CBO and allow them to participate in the city as well as other organizations’ HIV/AIDS prevention activities;
* PAC to continue supporting the cooperation with the referance center, making it easier for customers to approach and use the supporting services available at the city;
* Support to timely distribute items.